## ProjectSchedule
Decentralized Investment Platform for Stock-Exchange, Real-Estate and NFTs
This work is a continuation to our Mini Project - II titled "Tokenization of Customer Loyalty on Blockchain"
Mentor: Dr Rajendra Hegadi |  | 2023-01-09
Team: Karthik, Deepak, Krishna and Manoj |  | 1 |  |  | 2023-01-09 | [6 empty] | 2023-01-16 | [6 empty] | 2023-01-23 | [6 empty] | 2023-01-30 | [6 empty] | 2023-02-06 | [6 empty] | 2023-02-13 | [6 empty] | 2023-02-20 | [6 empty] | 2023-02-27
 | time axis 2023-01-09 to 2023-03-05
TASK | PROGRESS | START | END | DAYS | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Phase 1: Preliminary Project Preparations
Ideating various features to be added | 100% | 2023-01-09 | 2023-01-10 | 2
Ideation of Real-Estate Investment Feature studying property registrations of various states in India | 100% | 2023-02-19 | 2023-02-22 | 4
Preparation of Work Synopsis | 100% | 2023-01-13 | 2023-01-13 | 1
Sketching out the TechStack that shall be used for the Project | 100% | 2023-01-14 | 2023-01-14 | 1
Development of a Wireframe for the Web Application | 100% | 2023-01-15 | 2023-01-16 | 2
Exploratory Analysis of suitable solution for IPFS | 100% | 2023-03-13 | 2023-03-15 | 3
Listing out Security Loopholes and ideation of counter strategies | 100% | 2023-03-01 | 2023-03-04 | 4
Understanding the Procedure for Deployment on AWS | 100% | 2023-01-17 | 2023-01-17 | 1
Phase 2: Research Study and Surveys
Gathering Research Papers relevant to Reward Systems on Blockchain | 100% | 2023-01-18 | 2023-01-18 | 1
Preparing Literature Review papers gathered | 100% | 2023-01-19 | 2023-01-21 | 3
Research Survey on Loyalty programs from Investment Perspective | 100% | 2023-01-21 | 2023-01-21 | 1
Phase 3: Improvising and Debugging Previous Work
IPFS and Asynchronous Call bugs and glitches clearance | 100% | 2023-01-22 | 2023-01-22 | 1
Improvising Message Architecture and Styling | 100% | 2023-01-23 | 2023-01-24 | 2
Password Hashing | 100% | 2023-01-25 | 2023-01-25 | 1
Restriction of access to public functions in smart contracts | 100% | 2023-01-25 | 2023-01-25 | 1
Making the Platform responsive for Mobile-access | 100% | 2023-01-26 | 2023-01-29 | 4
Phase 4: Inclusion of New Features - UI
Creation of a Welcome Page and 404 Page | 100% | 2023-01-30 | 2023-01-31 | 2
Adding new roles and making necessary changes to login UI | 100% | 2023-02-05 | 2023-02-05 | 1
"Add Admin" and "Verified By" features | 100% | 2023-02-07 | 2023-02-07 | 1
Participants feature UI in Admin Panel | 100% | 2023-02-09 | 2023-02-09 | 1
Investor Judgement Score functionality UI in Participants Page | 100% | 2023-02-09 | 2023-02-09 | 1
Vendor and Registrar Broadcast UI in Admin Panel | 100% | 2023-02-11 | 2023-02-11 | 1
UI and JS for Transaction Logs functionality in Network Inspectors | 100% | 2023-02-13 | 2023-02-13 | 1
Share Document Auto-Generation feature | 100% | 2023-02-14 | 2023-02-16 | 3
Resale of Shares | 100% | 2023-02-16 | 2023-03-05 | 18
Inclusion of Real-Estate and NFTs pages in Investor Panel | 100% | 2023-02-17 | 2023-02-17 | 1
Skeleton UI Development of Vendor Panel | 100% | 2023-02-18 | 2023-02-18 | 1
Skeleton UI Development of Registrar Panel | 100% | 2023-02-19 | 2023-02-19 | 1
Implementing Google Maps in Registrar and Investor UI | 100% | 2023-03-10 | 2023-03-12 | 3
Implementing File Storage using IPFS with the help of web3storage | 100% | 2023-03-16 | 2023-03-18 | 3
NFTs UI in Vendor Panel | 100% | 2023-03-19 | 2023-03-25 | 7
Profile and Verifications Page in Registrar Panel | 100% | 2023-03-25 | 2023-03-31 | 7
Completion of Real-Estate and NFTs UI in Investor Panel | 100% | 2023-04-01 | 2023-04-05 | 5
Phase 5: Inclusion of New Features - Smart Contracts
Adding new roles by modifying users.sol | 100% | 2023-02-06 | 2023-02-06 | 1
"Add Admin" and "Verified By" features | 100% | 2023-02-07 | 2023-02-07 | 1
Participants feature in Admin Panel smart contract functions | 100% | 2023-02-10 | 2023-02-10 | 1
Investor Judgement Score functionality in Participants Page | 100% | 2023-02-11 | 2023-02-11 | 1
Vendor and Registrar Broadcast Smart Contract functions | 100% | 2023-02-12 | 2023-02-12 | 1
Verification ID generation and Verifying functionality in Solidity | 100% | 2023-02-16 | 2023-02-16 | 1
Real-Estate Investment Smart Contract Functionalities | 100% | 2023-04-06 | 2023-04-15 | 10
NFTs Smart Contract Functionalities | 100% | 2023-04-15 | 2023-04-25 | 11

## About
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. TimeSheet About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.